## Sheet1
Who's Task | Related User Story | Task Description | Initial Estimate | Hours Remaining
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Jake | CrewMate Login | Fix failing test in logging in. TryLoginFailsWithInvalidCredentials | 0.25 | 0
Jake | Crewmate AddStock | Change stock functionality to hold a type (Food/Other) | 0.5 | 0
Jake | Crewmate AddStock | Fix and add Unit test to all classes in storage package to achieve 100% branch coverage with new Stock type | 1.5 | 0
Jake | Crewmate AddStock | Fix and add Unit test to all viewmodel class that interact with stock to achieve 100% branch coverage with new Stock type | 1 | 0
Jake | Crewmate AddStock | Update GUI to allow user to select if the stock item is Food or Other | 0.25 | 0
Jake | QuarterMaster ViewStock Changes | Update model logic to be able to filter down to the minute instead of down to the day | 0.5 | 0
Jake | QuarterMaster ViewStock Changes | Update GUI to allow the user to filter down to the minute instead of down to the day while viewing stock changes | 0.25 | 0
Jake | QuarterMaster ViewStock Changes | Update Test cases to achieve 100% branch coverage for filtering to the minute | 0.5 | 0
Jake | QuarterMaster ViewStock Changes | Update the stock change model logic to have a stock change differentiate based off add or remove action type through an enum | 0.75 | 0
Jake | QuarterMaster ViewStock Changes | Update test cases to achieve 100% branch coverage in classes that interact with stock change | 1 | 0
Jake | QuarterMaster ViewStock Changes | Update the stock changes list, to list the type of action that occurred (added or removed) | 0.5 | 0
Jake | QuarterMaster ViewStock Changes | Update model logic to be able to filter by remove or add action type | 0.5 | 0
Jake | QuarterMaster ViewStock Changes | Update the GUI to be able to filter by remove or add action type while viewing stock changes | 0.25 | 0
Jake | QuarterMaster ViewStock Changes | Update and add test cases to achieve 100% branch coverage for filtering by remove or add action type | 0.5 | 0
Felix | QuarterMaster View Inventory | Update the Inventory class with logic to hold and manage a list of stock items | 0.5 | 0
Felix | QuarterMaster View Inventory | Implement compartment filtering logic within the Inventory model | 1 | 0
Felix | QuarterMaster View Inventory | Implement quality filtering logic within the Inventory model | 0.75 | 0
Felix | QuarterMaster View Inventory | Write Unit tests for the Inventory model to achieve 100% branch coverage | 0.75 | 0
Felix | QuarterMaster View Inventory | Create the ViewInventory ViewModel to show the stock list and available filters | 1 | 0
Felix | QuarterMaster View Inventory | Implement the function in the ViewModel to apply filters | 0.5 | 0
Felix | QuarterMaster View Inventory | Write Unit tests for the ViewInventory ViewModel to achieve 100% branch coverage | 0.75 | 0
Felix | QuarterMaster View Inventory | Design and build the main View Inventory GUI screen to display the list of stock | 0.5 | 0
Felix | QuarterMaster View Inventory | Implement data binding between the stock list in the ViewModel and the GUI ListView | 0.5 | 0
Markees | Cook can view food | Create the pantry UI | 1.5 | 1.5
Markees | Cook can view Food | Create the view model for pantry ui | 1.5 | 1.5
Markees | Cook can view food | add a way to Filter List View of Food Items list | 2 | 2
Markees | Cook can view Food | add a way to search list view by name | 1 | 1
Markees | Cook can view food | add test cases to achive 100% branch coverage | 2 | 2
Markees | Cook can get food | add Ability A way to take food away from the inventory via the pantry | 1 | 1
|  | Estimate Totals | 23.5 | 9 | 0 | 0 | 0